## Channels
Communities - example: https://consumer.huawei.com/pl/community/ | Regional newsletter |  | Press release https://mobinetrevija.si/druzinski-dogodek-z-govorecim-tomom-in-prijatelji-prinasa-nagrade/ https://www.feedit.cz/2022/06/02/huawei-zve-na-rodinnou-akci-plnou-barev-vyhrat-muzete-zajimave-ceny/
Social-media: https://www.facebook.com/HuaweimobileRO/posts/5204392896292662 |  | e-shops - https://consumer.huawei.com/tr/offer/ |  | Push

## 2022
Data |  | 29/08-4/09 | 5/09-11/09 | 10/10-16/10 | 17/10-23/10 | 24/10-30/10 | 31/10-6/11 | 7/11-13/11 | 14/11-20/11 | 21/11-27/11 | 28/11-4/12 | 05/12-11/12 | 12/12-18/12 | 19/12-25/12 | 26/12-1/1
|  | week 35 | week 36 | week 41 | week 42 | week 43 | week 44 | week 45 | week 46 | week 47 | week 48 | week 49 | week 50 | week 51 | week 52
Browser campaign activities | Blue push (Wednesday's) | week 42: 10/19/2022 France, Spain, Portugal, Romania, Croatia, Bulgaria; week 44: Countries - TBC; week 46: Countries - TBC; week 48: Countries TBD; week 50: countries TBD; week 52: countries TBD
| Gree push (Saturday's) | week 41: 2022-10-12; week 43: 2022-10-26; week 45: 2022-11-09; week 47: 2022-11-23
| Search Suggestions | week 41: All Europe
PPS Ads
AppGallery
| Communities | week 41: Always on campaing: home page - adjust banners regards prizes able to win in each round (try to simplify)
| Member Center | week 41: Always on campaign
| myHuawei App | week 41: Always on campaign
| Regional newsletter | week 41: 1 x Reg newsletter
| press release | week 41: 2 x regional press release: 1st - start campaign / 2nd - beg of 2023
| Social-media | week 41: TBC - per country
| e-shops (UK, ES IT, FR, DE, RO, TR, CS, PL) | week 41: Always on campaign

## 2023
Data |  | 29/08-4/09 | 5/09-11/09 | 2/1-8/1 | 9/1-15/1 | 16/1-22/1 | 23/1-29/1 | 30/1 - 5/2
|  | week 35 | week 36 | week 1 | week 2 | week 3 | week 4 | week 5
Browser campaign activities | Blue push (Wednesday's) | week 2: 19/10 content TBD; week 4: 2/11 content TBD | 16/11 content TBD |  | content TBD |  | content TBD |  | content TBD
| Gree push (Saturday's) | week 1: 2022-01-04; week 3: 2022-01-18; week 5: TBC
PPS Ads
AppGallery
Communities
| Member Center | week 1: 12/10 content TBD; week 3: 26/10 content TBD; week 5: 9/11 content TBD |  | 23/11 content TBD |  | content TBD |  | content TBD
myHuawei App
press release
e-shops (UK, ES IT, FR, DE, RO, TR, CS, PL)